PY 2023 Consolidated Annual Performance and Evaluation Report (CAPER)

Berkeley County

P. O. Box 6122

Moncks Corner, South Carolina 29461

Table of Contents

CR-05 - Goals and Outcomes	3

CR-10 - Racial and Ethnic composition of families assisted	8

CR-15 - Resources and Investments 91.520(a)	10

CR-20 - Affordable Housing 91.520(b)	17

CR-25 - Homeless and Other Special Needs 91.220(d, e); 91.320(d, e); 91.520(c)	19

CR-30 - Public Housing 91.220(h); 91.320(j)	21

CR-35 - Other Actions 91.220(j)-(k); 91.320(i)-(j)	23

CR-40 - Monitoring 91.220 and 91.230	26

CR-45 - CDBG 91.520(c)	29

CR-50 - HOME 24 CFR 91.520(d)	30

CR-58 - Section 3	32

## CR-05 - Goals and Outcomes

Progress the jurisdiction has made in carrying out its strategic plan and its action plan.  91.520(a)

This could be an overview that includes major initiatives and highlights that were proposed and executed throughout the program year.

Berkeley County is an entitlement community that was allocated CDBG funds for the first time by the U.S. Department of Housing and Urban Development (HUD) in PY 2021. In PY 2022, the County was also awarded annual HOME funds for the first time.  These funds are critical in enabling the County address the housing and community development objectives outlined by HUD, which include, but are not limited to: affirmatively furthering fair housing, affordable housing development and preservation, public improvements, and vital services for special needs and low- to moderate-income (LMI) populations. This PY 2023 Consolidated Annual Performance and Evaluation Report (CAPER) reports on the third year of the County’s 5-Year 2021-2025 Consolidated Plan.

Public Facilities: In PY 2023, the County continued to work on public facility improvements to neighborhood facilities such as the Berkeley County Senior Center, Tri-Community Center, Cross Community Center, American Legion Hut, Hell Hole Inc. Community Center, and the Bonneau Beach Civic Club.  These improvements increased accessibility, with projects including ADA improvements, expansion of rooms, and upgrades to kitchens.  The County also funded improvements at homeless shelters operated by Angel Wings Foundation and Changed Lives Ministry.  These shelter facility upgrades created more access for homeless youth and women.  Finally, the County funded water and sewer installations for future affordable housing developments.  In total, an estimated  20,908 LMI persons were assisted through these activities.

Slum & Blight Removal: The County is currently working on demolition activities to clear blighted properties in Jamestown, however these activities are still underway.  The removal of dilapidated structures and slums is expected to improve the health and safety standards in the area.

The County has been working to set up its HOME program, and affordable housing activities have not started yet.  The County continues to develop its program policy and procedures and identify activities to achieve its affordable housing goals in the plan.  In PY 2023 the County only utilized funds for admin, however it anticipates implementing the HOME program and opening applications in early PY 2024.

Comparison of the proposed versus actual outcomes for each outcome measure submitted with the consolidated plan and explain, if applicable, why progress was not made toward meeting goals and objectives.  91.520(g)

Categories, priority levels, funding sources and amounts, outcomes/objectives, goal outcome indicators, units of measure, targets, actual outcomes/outputs, and percentage completed for each of the grantee’s program year goals.

| Goal | Category | Source | Indicator | Unit of Measure | Expected – Strategic Plan | Actual – Strategic Plan | Percent Complete | Expected – Program Year | Actual – Program Year | Percent Complete |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1A Improve Access to Public Facilities | Non-Housing Community Development | CDBG | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 10000 | 24428 | 244.28% | 18900 | 20,908 | 110.62% |
| 1A Improve Access to Public Facilities | Non-Housing Community Development | CDBG | Homeless Person Overnight Shelter | Persons Assisted | 0 | 0 | 0.00% | 0 | 0 | 0.00% |
| 1A Improve Access to Public Facilities | Non-Housing Community Development | CDBG | Overnight/Emergency Shelter/Transitional Housing Beds added | Beds | 0 | 0 | 0.00% | 0 | 0 | 0.00% |
| 2A Reduce Slum & Blight in Residential Areas | Non-Housing Community Development | CDBG | Buildings Demolished | Buildings | 15 | 0 | 0.00% | 7 | 0 | 0.00% |
| 3A Provide Supportive Services for Special Needs | Non-Homeless Special Needs | CDBG | Public service activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 1000 | 0 | 0.00% |  |  |  |
| 3B Provide Vital Services for LMI Households | Non-Housing Community Development | CDBG | Public service activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 1000 | 1576 | 157.60% |  |  |  |
| 3C Provide for Improvements to Owner-occupied Hous | Affordable Housing | CDBG | Homeowner Housing Rehabilitated | Household Housing Unit | 10 | 0 | 0.00% |  |  |  |
| 4A Affordable Owner-Occupied Housing Opportunities | Affordable Housing | HOME | Homeowner Housing Added | Household Housing Unit | 8 | 0 | 0.00% | 2 | 0 | 0.00% |
| 4A Affordable Owner-Occupied Housing Opportunities | Affordable Housing | HOME | Homeowner Housing Rehabilitated | Household Housing Unit | 40 | 0 | 0.00% | 10 | 0 | 0.00% |
| 4B Affordable Rental Housing Opportunities | Affordable Housing | HOME | Rental units constructed | Household Housing Unit | 5 | 0 | 0.00% |  |  |  |
| 4B Affordable Rental Housing Opportunities | Affordable Housing | HOME | Rental units rehabilitated | Household Housing Unit | 10 | 0 | 0.00% |  |  |  |

Table 1 - Accomplishments – Program Year & Strategic Plan to Date

Assess how the jurisdiction’s use of funds, particularly CDBG, addresses the priorities and specific objectives identified in the plan, giving special attention to the highest priority activities identified.

PY 2023 is the third program year of the 2021-2025 Consolidated Plan, and the County has identified the following as priority needs for the community: Expand & Improve Public Facilities, Reduce Slum & Blight in Residential Areas, Public Services & Quality of Life Improvements and Affordable Housing Development and Preservation.  CDBG funded activities must address one of these needs as well as primarily benefit LMI persons or special needs populations.

In PY 2023, the County worked to address the needs of the community through public facility improvements and demolition activities.  These funded activities were developed through the community’s desire to see impacts made towards the identified priority needs in the Consolidated Plan.  The use of CDBG funds for the program year is outlined below:

Public Facility and Infrastructure Improvements: $1,307,609.82 (80.8%)

Demolition: $26,000.00 (1.6%)

Public Services: $11,400.00 (0.7%)

Administration of the CDBG Program: $273,441.85 (16.9%)

Total CDBG in PY 2023: $1,618,451.67

PY 2023 PR-23 and CR-05 Goals and Outcomes Table Comparison

1A Improve Access to Public Facilities

The County had a goal to assist 18,900 individuals living in low/mod areas with public facility improvements and exceeded this goal with an estimated 20,908 persons assisted. These activities included neighborhood center improvements at the Tri-Community Center, Cross Community Center, the American Legion Hut, the Bonneau Beach Civic Club, A Fathers Place, Hell Hole Community Center, and the Berkeley County Senior Center.  The County also funded facility improvements at homeless shelters run by Angel Wings Foundation and Changed Lives Ministry.

2A Reduce Slum & Blight in Residential Areas

The County had a goal to demolish 7 buildings in Jamestown, and these activities are still underway.  The County anticipates that these activities will be completed and reported in the next CAPER.

3A Provide Supportive Services for Special Needs

There were no outcomes for this goal in PY 2023.

3B Provide Vital Services for LMI Households

There were no outcomes for this goal in PY 2023.

3C Provide for Improvements to Owner-occupied Housing

There were no outcomes for this goal in PY 2023.

4A Affordable Owner-Occupied Housing Opportunities

The County had a goal to add 2 housing units and rehab 10 homeowner housing units in PY 2023.  Unfortunately this goal has not been achieved yet. This goal is associated with the new HOME program which the County is still setting up.  Funds that have been programmed into these activities are still underway, and the County anticipates reporting on these outcomes in the next CAPER.

4B Affordable Rental Housing Opportunities:

There were no outcomes for this goal in PY 2023. .

## CR-10 - Racial and Ethnic composition of families assisted

Describe the families assisted (including the racial and ethnic status of families assisted). 91.520(a)

|  | CDBG | HOME |
| --- | --- | --- |
| White | 230 | 0 |
| Black or African American | 201 | 0 |
| Asian | 0 | 0 |
| American Indian or American Native | 1 | 0 |
| Native Hawaiian or Other Pacific Islander | 0 | 0 |
| Total | 432 | 0 |
| Hispanic | 5 | 0 |
| Not Hispanic | 428 | 0 |

Table 2 – Table of assistance to racial and ethnic populations by source of funds

Narrative

DATA NOTE: The table above does not account for individuals identifying as “other multi-racial,” nor does it include a category for activities that provide a “low/mod area-wide benefit,” which are frequently associated with public facility or infrastructure improvements. As a result, the racial or ethnic data presented in the table may not fully represent the diversity of individuals and groups served by the CDBG program.

According to the most recent 2018-2022 American Community Survey 5-Year Estimates (DP-05), the population of Berkeley County was 231,419, with 64.3% identifying as White, 23.3% as Black or African American, and 2.4% as Asian. Those identifying as “Some other race” comprised 3.3% of the population, while individuals identifying with “Two or more races” made up 6.3%. Additionally, 7.3% of the population identified as ethnically Hispanic. Although CDBG funds primarily target low- to moderate-income individuals and households, the County is committed to recording and tracking investments in minority groups whenever feasible.

CDBG: The table above reports a total of 432 individuals by race; however, the actual total was 433, as the IDIS reporting system does not include a category for “other multi-racial.” There was one individual reported as “other multi-racial.” Among those assisted with CDBG funds, approximately 53.1% were White, 46.4% were Black or African American, and 0.2% were identified as “other or multiple races.” Additionally, 1.2% of all persons assisted with CDBG funds identified as ethnically Hispanic. Compared to the general population, the CDBG program has effectively served Black or African American individuals; however, there is a need to increase outreach and support to Asian and Hispanic beneficiaries.

HOME: This was the second year that Berkeley County received HOME funds. While the program has not yet recorded any accomplishments, the County plans to increase the affordable housing stock through activities such as the addition of homeowner housing and housing rehabilitation. These efforts will be documented and reported in future CAPER reports.

Housing Needs Assessment

The Housing Needs Assessment in the County’s Consolidated Plan evaluates whether any racial or ethnic groups, categorized by income, face disproportionate challenges with regards to housing problems, severe housing problems and cost burden. Households with housing problems are those that reside in units lacking complete kitchen and plumbing facilities as well as overcrowding (more than one person per room) and cost burden (spending 30% or more of income on housing per month).  Households with severe housing problems are those that reside in units lacking complete kitchen and plumbing facilities as well as severely overcrowded homes (more than 1.5 person per room) and severe cost burden (spending 50% or more of income on housing per month).

NA-15: The Needs Assessment reveals that Hispanic households face housing problems at a disproportionate rate across multiple income categories. Additionally, American Indian households within the 30-50% Area Median Income (AMI) range and Asian households within the 50-80% AMI range also experience housing problems disproportionately.

NA-20: When assessing severe housing problems, Hispanic households continue to be disproportionately impacted across several income levels. Furthermore, both Asian and American Indian households within the 30-50% AMI bracket experience severe housing problems at a disproportionate rate.

NA-25: Regarding housing cost burden, American Indian and Hispanic households are disproportionately affected, making them more likely to experience housing cost burdens.

Recognizing these disparities, the County has identified the need to address housing problems for Hispanic, Native American, and Asian households as outlined in the Needs Assessment of the Consolidated Plan. This insight is being actively considered as the County initiates its HOME program aimed at developing affordable housing in the area. It is important to note, however, that the number of Native American and Asian households in the County is relatively small.

## CR-15 - Resources and Investments 91.520(a)

Identify the resources made available

| Source of Funds | Source | Resources Made Available | Amount Expended During Program Year |
| --- | --- | --- | --- |
| CDBG | public - federal | 1,284,550 | 1,618,452 |
| HOME | public - federal | 552,117 | 44,009 |

Table 3 - Resources Made Available

Narrative

The table above shows the total resources made available to the County from HUD in PY 2023.  These sources of funds were from the CDBG and HOME program.

In PY 2023,  the county had $1,284,550 available in CDBG funds from the annual allocation.  According to the PR-07, in PY 2023 the County expended $1,618,452.  According to the PR-07 report, the County expended a total of $1,618,452 during this period. This amount includes funds allocated in previous Action Plans that were expended in PY 2023. Below is a breakdown of CDBG entitlement (EN) funds spent by priority.

Public Facility and Infrastructure Improvements: $1,307,609.82 (80.8%)

Demolition: $26,000.00 (1.6%)

Public Services: $11,400.00 (0.7%)

Administration of the CDBG Program: $273,441.85 (16.9%)

Total CDBG in PY 2023: $1,618,451.67

PY 2023 was the second year in which the County was awarded HOME funds.  In PY 2023,  $552,117 was made available in HOME funds from the annual allocation.  According to the PR-07 report, the County expended $44,009 on administrative costs associated with launching and managing the program. The County plans to initiate program activities in the upcoming program year.

Identify the geographic distribution and location of investments

| Target Area | Planned Percentage of Allocation | Actual Percentage of Allocation | Narrative Description |
| --- | --- | --- | --- |
| Countywide | 100 | 100 | Public facilities, demolition, public services and admin. |

Table 4 – Identify the geographic distribution and location of investments

Narrative

Berkley County implements its projects countywide based on its priority needs and income of beneficiaries. The County places a strong emphasis on supporting low- and moderate-income households, as well as special needs populations throughout the area. Funding is not allocated solely based on geographic criteria; instead, individuals or households must meet specific income qualifications to receive direct assistance from CDBG or HOME program activities and services. For eligible public facilities and infrastructure improvement activities, the County targets census block groups identified as low- to moderate-income areas and focuses on facilities that serve special needs populations, such as the homeless, elderly, or persons with disabilities.

Leveraging

Explain how federal funds  leveraged additional resources (private, state and local funds), including a description of how matching requirements were satisfied, as well as how any publicly owned land or property located within the jurisdiction that were used to address the needs identified in the plan.

Berkeley County is committed to expanding resources to address the community's needs effectively. The strategic use of federal Community Development Block Grant (CDBG) funds plays a pivotal role in leveraging additional resources, including private, state, and local funds. CDBG-funded activities often attract supplementary funding, enhancing the scope and impact of these projects.

Recently, the County secured federal funding from the Department of Justice to address high-crime areas and support victims of crimes. Additionally, state funding has been obtained through grants from the South Carolina Department of Health and Environmental Control, the South Carolina Department of Commerce, the South Carolina Rural Infrastructure Authority, and the South Carolina Department of Parks and Recreation for various community development and infrastructure improvements across the County.

Publicly owned land or property located used to address the needs identified in the plan

The various Berkeley County libraries provide a space for community participation with the County when meeting with the public on CDBG programming. The Berkeley County Senior Center in Goose Creek received funds to improve the facility.  Although the County does not own most public facilities funded for improvements in PY 2023, it should be noted that the Jamestown Recreational Park is owned by the Town of Jamestown, and the American Legion Hut is owned by the Town of St. Stephen.

HOME Match: All HOME Participating Jurisdictions, including Berkeley County, must contribute or match no less than 25% for each dollar of HOME funds spent on affordable housing. As a PJ draws funds for HOME, they incur a match liability, which must be satisfied by the end of each federal fiscal year.  In FY 2023, the County’s HOME Match liability was $0 as there were no HOME funds spent on housing activities.  The PR-33 HOME Matching Liability Report has confirmed this with a $0 match liability amount for the program year.

HOME WBE/MBE: There were no contracts awarded to minority or women-owned businesses in PY 2023.

HOME Program Income: No HOME program income funds were received or expended in PY 2023. The County contributed $233,132 in HOME program income funds in the previous program year 2022 since that year’s annual allocation in did not meet the initial threshold of $750,000 for the County to become a HOME PJ.  These funds are displayed as the balance on hand at the start of the program year.

| Fiscal Year Summary – HOME Match |  |
| --- | --- |
| 1. Excess match from prior Federal fiscal year | 0 |
| 2. Match contributed during current Federal fiscal year | 0 |
| 3 .Total match available for current Federal fiscal year (Line 1 plus Line 2) | 0 |
| 4. Match liability for current Federal fiscal year | 0 |
| 5. Excess match carried over to next Federal fiscal year (Line 3 minus Line 4) | 0 |

Table 5 – Fiscal Year Summary - HOME Match Report

| Match Contribution for the Federal Fiscal Year |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project No. or Other ID | Date of Contribution | Cash (non-Federal sources) | Foregone Taxes, Fees, Charges | Appraised Land/Real Property | Required Infrastructure | Site Preparation, Construction Materials, Donated labor | Bond Financing | Total Match |
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |

Table 6 – Match Contribution for the Federal Fiscal Year

HOME MBE/WBE report

| Program Income – Enter the program amounts for the reporting period |  |  |  |  |
| --- | --- | --- | --- | --- |
| Balance on hand at begin-ning of reporting period $ | Amount received during reporting period $ | Total amount expended during reporting period $ | Amount expended for TBRA $ | Balance on hand at end of reporting period $ |
| 233,132 | 0 | 0 | 0 | 233,132 |

Table 7 – Program Income

Minority Business Enterprises and Women Business Enterprises – Indicate the number and dollar value of contracts for HOME projects completed during the reporting period

|  | Total | Minority Business Enterprises |  |  |  | White Non-Hispanic |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Alaskan Native or American Indian | Asian or Pacific Islander | Black Non-Hispanic | Hispanic |  |

| Contracts |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |
| Dollar Amount | 0 | 0 | 0 | 0 | 0 | 0 |

| Sub-Contracts |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |
| Dollar Amount | 0 | 0 | 0 | 0 | 0 | 0 |

|  | Total | Women Business Enterprises | Male |
| --- | --- | --- | --- |

| Contracts |  |  |  |
| --- | --- | --- | --- |
| Number | 0 | 0 | 0 |
| Dollar Amount | 0 | 0 | 0 |

| Sub-Contracts |  |  |  |
| --- | --- | --- | --- |
| Number | 0 | 0 | 0 |
| Dollar Amount | 0 | 0 | 0 |

Table 8 - Minority Business and Women Business Enterprises

Minority Owners of Rental Property – Indicate the number of HOME assisted rental property owners and the total amount of HOME funds in these rental properties assisted

|  | Total | Minority Property Owners |  |  |  | White Non-Hispanic |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Alaskan Native or American Indian | Asian or Pacific Islander | Black Non-Hispanic | Hispanic |  |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |
| Dollar Amount | 0 | 0 | 0 | 0 | 0 | 0 |

Table 9 – Minority Owners of Rental Property

Relocation and Real Property Acquisition – Indicate the number of persons displaced, the cost of relocation payments, the number of parcels acquired, and the cost of acquisition

|  | Number | Cost |
| --- | --- | --- |
| Parcels Acquired | 0 | 0 |
| Businesses Displaced | 0 | 0 |
| Nonprofit Organizations Displaced | 0 | 0 |
| Households Temporarily Relocated, not Displaced | 0 | 0 |

| Households Displaced | Total | Minority Property Enterprises |  |  |  | White Non-Hispanic |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Alaskan Native or American Indian | Asian or Pacific Islander | Black Non-Hispanic | Hispanic |  |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |
| Cost | 0 | 0 | 0 | 0 | 0 | 0 |

Table 10 – Relocation and Real Property Acquisition

## CR-20 - Affordable Housing 91.520(b)

Evaluation of the jurisdiction's progress in providing affordable housing, including the number and types of families served, the number of extremely low-income, low-income, moderate-income, and middle-income persons served.

|  | One-Year Goal | Actual |
| --- | --- | --- |
| Number of Homeless households to be provided affordable housing units | 0 | 0 |
| Number of Non-Homeless households to be provided affordable housing units | 12 | 0 |
| Number of Special-Needs households to be provided affordable housing units | 0 | 0 |
| Total | 12 | 0 |

Table 11 – Number of Households

|  | One-Year Goal | Actual |
| --- | --- | --- |
| Number of households supported through Rental Assistance | 0 | 0 |
| Number of households supported through The Production of New Units | 2 | 0 |
| Number of households supported through Rehab of Existing Units | 10 | 0 |
| Number of households supported through Acquisition of Existing Units | 0 | 0 |
| Total | 12 | 0 |

Table 12 – Number of Households Supported

Discuss the difference between goals and outcomes and problems encountered in meeting these goals.

In PY 2023, Berkeley County did not provide funding directly toward the development of new affordable housing or housing rehabilitation activities.  HOME funds were awarded for only the second time in PY 2023 and the County is still establishing the program and identifying activities and eligible households to be assisted.

Discuss how these outcomes will impact future annual action plans.

The County will continue to address affordable housing development and preservation as it’s been identified as a priority by the County and its residents.  In the previous program year, the County’s Consolidated Plan was Substantially Amended to include the HOME grant and affordable housing goals for both homeowners and renters in the areas of new housing development and housing rehab.  Future Annual Action Plans will reflect the changes made in the Substantial Amendment to the Consolidated Plan.

Include the number of extremely low-income, low-income, and moderate-income persons served by each activity where information on income by family size is required to determine the eligibility of the activity.

| Number of Households Served | CDBG Actual | HOME Actual |  |
| --- | --- | --- | --- |
| Extremely Low-income | 0 | 0 |
| Low-income | 0 | 0 |
| Moderate-income | 0 | 0 |
| Total | 0 | 0 |

Table 13 – Number of Households Served

Narrative Information

In PY 2023, Berkeley County did not complete any new affordable housing developments or rehabilitate existing housing units, resulting in no households being reported.  However, the County’s plan includes the allocation of HOME funds for homeowner housing construction and owner-occupied housing rehab.  The County anticipates reporting these activity accomplishments in future CAPER reports.

Worst Case Needs

Worst case needs refer to extremely low-income households that are at imminent risk of homelessness and are in need of affordable housing or emergency assistance.  Currently the County has not yet assisted any extremely low-income households with HOME funds, as the program is still in development.  In the future, the County will seek to help those with worst case needs.

The County also did not specifically report any persons with a disability through affordable housing programs in the program year.  In the future, when funds become available to assist residents with affordable housing programs, the County will prioritize accommodating the needs of households with disabilities, making reasonable adjustments to ensure their needs are met.

## CR-25 - Homeless and Other Special Needs 91.220(d, e); 91.320(d, e); 91.520(c)

Evaluate the jurisdiction’s progress in meeting its specific objectives for reducing and ending homelessness through:

Reaching out to homeless persons (especially unsheltered persons) and assessing their individual needs

The County is a member of the Lowcountry Continuum of Care, the local Continuum of Care (CoC). The City of Charleston is the largest population center in the area and borders Berkeley County. While the homeless population is relatively high within Charleston, Berkeley County only reported 26 homeless persons in the 2020 Point-in-Time Count. This is in part due to the challenges of reporting homelessness in rural areas, as much of Berkeley County is unincorporated and rural. County numbers have not been updated since the 2020 Point int Time Count, but It is expected that the actual rates of homelessness in the County are much higher.  The County relies  on service providers and nonprofits to identify individuals experiencing homelessness in the County and connect them with appropriate services.

Lowcountry CoC utilizes the Homeless Management Information System (HMIS) to track intakes through the Coordinated Entry System.  Data from the centralized HMIS and intakes into the Coordinated Entry System provide important details of individuals and families experiencing homelessness (including household composition, ages, disability status, length of time homeless, and overall vulnerability) inform programs and agencies of the needs and recommended housing interventions for this population in Berkeley County and across the six other counties in the CoC.  This process is intended to be done as quickly as possible to make homelessness rare, brief, and nonrecurring.

Addressing the emergency shelter and transitional housing needs of homeless persons

As reported by the Lowcountry Continuum of Care in HUD’s 2023 COC Homeless Assistance Programs Housing Inventory Count Report, the CoC’s network offers more than 250 emergency shelter beds for homeless persons in the region.  None of these are physically located in Berkeley County, however One80 Place, My Sister’s House, and the Formation Project offer their shelter services to Berkeley County residents experiencing homelessness or fleeing domestic violence or human trafficking.

The County has worked to identify partners that can address the emergency and transitional housing needs of individuals experiencing homeless in the County.  In PY 2023 the County completed public facility improvements at to Changed Lives Ministry and Angel Wings Foundation. Changed Lives Ministry provides a transitional rehabilitation program to men and women struggling with addiction.  Angel Wings Foundation in Moncks Corner works with homeless youth.

Helping low-income individuals and families avoid becoming homeless, especially extremely low-income individuals and families and those who are:  likely to become homeless after being discharged from publicly funded institutions and systems of care (such as health care facilities, mental health facilities, foster care and other youth facilities, and corrections programs and institutions);  and,  receiving assistance from public or private agencies that address housing, health, social services, employment, education, or youth needs

The County recognizes that low-income individuals and families who have been recently discharged or are about to be discharged from public institutions and/or systems of care are at high risk of becoming homeless.  The County relies on the network of experienced service providers in the Tri-County area to address the needs of these individuals and families.  These  providers include Florence Crittenton, Family Promise, One80Place, Charleston Trident Urban League, Origin, Palmetto Community Action Partnership, and Changed Lives Ministries.

Carolina Youth Development Center offers support services that provide for personal growth, leadership advancement, case management, promote supportive group environments and overall health and wellness. Programs include the Strengthening Families parenting program, a 14-week evidence-based family skills training program; Keep Connected relationship building workshop designed to help parents and their teens express care, challenge growth, provide support, share power, and expand possibilities; and Scholar Centric, a science-based, standards aligned curriculum proven to build the resiliency skills students need to persevere and succeed in school.

Helping homeless persons (especially chronically homeless individuals and families, families with children, veterans and their families, and unaccompanied youth) make the transition to permanent housing and independent living, including shortening the period of time that individuals and families experience homelessness, facilitating access for homeless individuals and families to affordable housing units, and preventing individuals and families who were recently homeless from becoming homeless again

Berkeley County and the Lowcountry CoC are committed to helping homeless persons, especially those who are chronically homeless and homeless families with children make the transition from homelessness to permanent housing and independent living. The issues with chronically homeless persons can be many and/or interrelated and therefore the County and the CoC will work together with its network of service providers to help them receive all the referrals and resources they require to keep them sheltered and return to independent living.

In the past few years, the County has awarded funding to Habitat for Humanity to purchase and prepare land for the development of affordable housing. The projects are currently underway, and when they are complete with constructed homes, 10 affordable housing units will be provided to low-income individuals and families in Berkeley County. Additionally, when the County begins its HOME program, additional permanent, affordable housing units will be made available in the County.

## CR-30 - Public Housing 91.220(h); 91.320(j)

Actions taken to address the needs of public housing

The local housing authority operating in Berkeley County is the South Carolina Regional Housing Authority No. 3 (SCRHA3).  SCRHA3 creates stable housing for LMI families in the region. The mission of the SC Regional Housing Authority No. 3 is to provide all the necessary tools for a family to obtain and maintain affordable housing and home ownership in a safe, sanitary, and decent manner. In carrying out this mission, SCRHA3 creates partnerships with various community resources to ensure a complete needs fulfillment for families with the purpose of assisting them in the opportunity of becoming self-sufficient.  It promotes housing stability by providing all the necessary tools available to help them maintain this stability.  Two of the main strategies involved are helping residents find suitable employment and lifestyle skill development.  SCRHA3 manages two public housing complexes in the County with 78 units at St. Francis Villa Apartments in Moncks Corner and 50 units at Belangia Apartments in St. Stephen.  SCRHA3 also administers over 1,300 Housing Choice Vouchers (HCV) across the seven counties it serves, including Berkeley County.

Actions taken to encourage public housing residents to become more involved in management and participate in homeownership

SCRHA3 offers supportive services that help to increase residents’ involvement with activities within the community.  Supportive services provide opportunities for personal growth, leadership advancement and community engagement; resident job training and employment placement; case management and supportive group environments; and health and wellness initiatives.  These programs include:

Youth Enrichment Scholarships (YES): This program provides assistance with registration fees to connect residents with community and school-based activities and resources.

Benefit Access: This program provides access to resources needed by families to achieve and maintain self-sufficiency.

Resident Training Program: This program provides job training and employment opportunities through hands-on experience and job coaching.

Family Self-Sufficiency (FSS): Family Self Sufficiency (FSS) is a HUD program that allows residents of HCV and public housing to build financial assets as the household increases earned income from wages. Participation generally lasts five (5) years, during which participants identify educational, professional and personal goals. As a part of the FSS program, participants work with the HCV department staff to develop a plan that outlines specific activities needed to achieve their economic self-sufficiency goals. Throughout the program, the staff monitors participants' progress and helps them move toward self-sufficiency.

The Lease Purchase Program: Through this program, a select number of houses where a potential homebuyer can move in to while they are working to become mortgage ready.  During the rental period, the homebuyer must actively participate in housing counseling and will pay rent based upon their income.  Once the potential homeowner becomes mortgage ready, they will begin the process to purchase the home.  An amount of $50 from each month’s rent is set aside for the potential homebuyer to use for down payment and closing cost assistance for the purchase of that home.  SCRHA3 partners with Southeastern Housing and Community Development’s Financial Resource Center to provide this program.

Actions taken to provide assistance to troubled PHAs

SCRHA3 is not designated as troubled.

## CR-35 - Other Actions 91.220(j)-(k); 91.320(i)-(j)

Actions taken to remove or ameliorate the negative effects of public policies that serve as barriers to affordable housing such as land use controls, tax policies affecting land, zoning ordinances, building codes, fees and charges, growth limitations, and policies affecting the return on residential investment. 91.220 (j); 91.320 (i)

Berkeley County has implemented several important public policies to address the housing needs of Berkeley County residents and demonstrate its commitment to expanding affordable housing in the community. The Analysis of Impediments completed in March of 2021 identified public policies that have and can continue to make positive impacts on the affordable housing market include:

- Incentives for Housing Preservation and Renovation – The County has enacted a Special Property Tax Assessment Ordinance for rehabilitating historic properties (Ordinance 19-04-08). This supports the county’s policy to protect existing communities and neighborhoods from physical deterioration.

- Sustainable Infrastructure Funding – The Transportation Sales Tax program was enacted to help support street infrastructure to accommodate new housing. This program can reduce the cost of constructing new housing.

- Progressive Planning Approach – The One Berkeley Comprehensive Plan incorporates scenario planning. This approach considers community desires and the impacts and trade-offs to provide more informed decision-making. County planning policies also support a range of residential lot sizes and diverse housing types that can result in a wider range of home values.

- Presence of Intergovernmental Cooperation – Many jurisdictions lack intergovernmental cooperation that can result in a disconnect between services and facilities. The county practices coordination planning with the Berkeley County School District to anticipate the need for additional school facilities.

- Encourage Housing Density – The 2018 Comprehensive Plan Update encourages clustering of residential lots through a density bonus approach, and low-density development supports diverse housing choices. New residential development planning policies also emphasizes linkages to public transportation that will enable better access to employment opportunities.

- Availability of an Affordable Housing Financing Mechanism - The Lowcountry Housing Trust (LHT) finances the production of affordable housing.  Today, financing offered by LHT includes development loans for affordable housing, including land acquisition, predevelopment, infrastructure, construction, and mini-perm loans. The county also promotes other housing partnerships and home buyer education programs.

- Commitment to Reducing Regulatory Barriers – The County Council and Planning Commission are working to identify and reduce regulatory barriers to affordable housing.

Actions taken to address obstacles to meeting underserved needs.  91.220(k); 91.320(j)

The Analysis of Impediments identified affordable-housing related impediments for the County. The County addressed affordable housing in PY 2023 by providing funding to Habitat for Humanity to create infrastructure for affordable housing. When Habitat for Humanity completes the construction of the houses on the property, 10 LMI households become homeowners.

Expanding and Improving Facilities was identified as a priority need in the 2021 Consolidated Plan, as neighborhood facilities, senior centers and parks help to improve the lives of individuals living in low/mod areas. In PY 2023, The County provided CDBG funds to multiple facility improvements across the County.  These activities included neighborhood center improvements at the Tri-Community Center, Cross Community Center, the American Legion Hut, the Bonneau Beach Civic Club, A Fathers Place, Hell Hole Community Center, and the Berkeley County Senior Center.  The County also funded facility improvements at homeless shelters run by Angel Wings Foundation and Changed Lives Ministry.

Actions taken to reduce lead-based paint hazards. 91.220(k); 91.320(j)

The County did not undertake any housing activities in PY 2023 that required the mitigation of lead-based paint hazards.  When the County does undertake housing activities, it will follow all regulations as required by HUD and the Residential Lead-Based Paint Hazard Reduction Act of 1992.  A certified inspection of a structure built prior to 1978 will determine the presence of lead-based paint.  If lead-based paint is found to exist, a risk assessment is conducted to determine the type, severity and location of the hazards.  The findings of the risk assessment may direct abatement as the solution to best protect children from lead exposure.  The County makes HUD Lead Hazard Information pamphlets available to all citizens, upon request.

Actions taken to reduce the number of poverty-level families. 91.220(k); 91.320(j)

The County allocated previous program year 2022 CDBG funding for public services at Helping Hands of Goose Creek. Helping Hands of Goose Creek is an emergency assistance center and food pantry serving poverty-level individuals and families who are experiencing a life crisis situation.  There were 1,576 individuals assisted with this activity.

CDBG funds were utilized to assist Landmarks for Families (fka Carolina Youth Development Center) with facility improvements in Berkeley County. The agency works to reduce the number of families who are experiencing poverty. The agency has experience utilizing CDBG funds to support housing for youth experiencing homelessness, for youth transitioning out of foster care into adulthood, and a summer literacy program for children in low-income households.

Actions taken to develop institutional structure. 91.220(k); 91.320(j)

Berkeley County continues to work with organizations that address the various needs of the citizens of the County.  Each funded organization is provided an overview of the CDBG program, and the County monitors and provides assistance as needed throughout the program year.  The County also works with the South Carolina Regional Housing Authority No. 3 (PHA) and Lowcountry Continuum of Care (CoC) in planning to meet the needs of its citizens.

In PY 2023, the County took the following actions to further develop and enhance institutional structure: Participated in HUD webinars to enhance knowledge of the CDBG program and cross-cutting requirements; Worked with sub-recipient organizations to train their staff on the CDBG administrative requirements as needed; and developed relationships with neighboring jurisdictions and non-profit organizations that carry out community development programs.

Actions taken to enhance coordination between public and private housing and social service agencies. 91.220(k); 91.320(j)

Berkeley County continues to coordinate with the South Carolina Regional Housing Authority No. 3 to meet the needs of citizens in publicly assisted housing in the County.  In PY 2022, the County received HOME funding for the first time. The County spent the program year developing the program and will work closely with private housing agencies to develop affordable housing and rehabilitate owner-occupied homes of low-income households. The County will open HOME applications for development projects in PY 2024.

Identify actions taken to overcome the effects of any impediments identified in the jurisdictions analysis of impediments to fair housing choice.  91.520(a)

In March 2021, the County completed an Analysis of Impediments. Since the completion of the analysis, the County has taken the following action:

- The Berkeley County website has basic information, the local hotline, and links to related local, state, and federal sources of information on fair housing. The Joint Analysis of Impediments to Fair Housing Choice is also available on the website.

- CDBG funds were provided to Habitat for Humanity to create infrastructure for the development of affordable housing.

- The HOME program was started to address the need for more affordable housing, and for the preservation of the affordable housing stock.

## CR-40 - Monitoring 91.220 and 91.230

Describe the standards and procedures used to monitor activities carried out in furtherance of the plan and used to ensure long-term compliance with requirements of the programs involved, including minority business outreach and the comprehensive planning requirements

Berkeley County’s monitoring process involves continuous communication with the subrecipient, project manager and evaluation of financial records and is used to evaluate regulatory performance in the administrative, financial and programmatic areas of CDBG funded activities. Such a process involves frequent telephone/email contacts, written communications, analysis of reports and audits, and periodic meetings. County staff provide technical assistance as needed to any subrecipient or internal project manager.

Monitoring consists of both desktop and on-site reviews.  On-site reviews include an in-depth review of project and client files. Each grant close-out requires and on-site monitoring review.  Quarterly desktop monitoring includes a review of contractual commitments, financial documentation, determination of cost eligibility, drawdown rates, and outcome/performance measurement review.  Through on-site and desktop monitoring, the monitor can determine whether the participant's performance meets program requirements and improve performance by providing guidance and making recommendations. The specific purposes of monitoring are to:

- Validate the accuracy of information presented by the applicant;

- Determine compliance for those activities where there is sufficient information to make eligibility and/or national objective determinations;

- Evaluate the reasonableness of judgments made for those activities that necessarily involve high levels of program participant judgment;

- Establish the subrecipient’s ability to ensure that activities carried out meet compliance requirements;

- Verify the accuracy of the program participant's records; and,

- Identify apparent causes of any problem(s) and offer recommendations for corrective actions.

Due to the critical need to disburse CDBG funds promptly, County staff closely monitor each project's progress to ensure timely execution. Subrecipients that do not spend their grant funds in a timely manner are strongly encouraged to expedite spending or risk losing current and future funding through the County's HUD programs. This monitoring process also helps identify high-risk projects or applicants that may require additional oversight in the coming years.

Comprehensive Planning Requirements

The comprehensive planning requirements include the community planning and development process of the 5-Year ConPlan, subsequent AAPs, and CAPERs as per 24 CFR 91 Subpart A, C & F.  Citizen participation is a vital part of the consolidated plan process, and the County will make sure to follow its HUD approved Citizen Participation Plan (CPP) which helps guide staff to gather community input which is an essential component in identifying the priority housing and community development needs in the County. The ConPlan is developed every 5 years, with identified priority needs and goals to address these needs.  Each year of the 5-Year plan, the County develops an AAP which identifies the projects and activities that will address and further the goals of the plan.  This plan is required to be submitted to and approved by HUD each year to receive CDBG funding annually.  At the end of each AAP program year, the County will report on the accomplishments and performance of the program through the CAPER (performance report).  Citizen participation is required in the development of each of these stages as per 24 CFR 91.105. PY 2023 is the third year of the County 2021-2025 Consolidated Plan.

Citizen Participation Efforts for the 2023 AAP

A public hearing was held to discuss the 2023 AAP. The hearing was held on April 5, 2023 at 5:00 PM in the County Council Assembly Room in the Administrative Building, 1003 Highway 52, Moncks Corner, SC 29461.  There were no comments received at the public hearing. A public comment period was also held from April 13, 2023 through May 13, 2023 and the plan was available online at www.berkeleycountysc.gov, or at the County Grants Administration office, located at the Administrative Building, 1003 Highway 52, Moncks Corner, SC 29461.  Written comments could be submitted to lechele.brown@berkeleycountysc.gov or delivered to the Grants Administration office. There was one comment received from a member of the public in favor to not fund religious institutions.  There were no other comments made.

Citizen Participation Plan 91.105(d); 91.115(d)

Describe the efforts to provide citizens with reasonable notice and an opportunity to comment on performance reports.

The purpose of the citizen participation process is to actively encourage citizens, particularly low- and moderate-income households, to participate in the planning of the Consolidated Plan, the Annual Action Plan (AAP), the development of the Consolidated Annual Performance Evaluation Report (CAPER) and any required submission of substantial amendments to those plans. Berkeley County works to ensure community stakeholders and County citizens have adequate opportunities to participate in this planning process.

PUBLIC COMMENT PERIOD: Citizens were invited to review and make comments on the draft 2023 CAPER. The draft CAPER was available for (15) fifteen days beginning Tuesday August 27th to Monday September 9th TBD, and comments concerning the draft CAPER had to be received by TBD. The draft CAPER was available online at www.berkeleycountysc.gov, and at the County’s Grants Administration office, located at the Administrative Building, 1003 Highway 52, Moncks Corner, SC 29461.  Written comments could be submitted to the County’s Grants Specialist, at lechele.brown@berkeleycountysc.gov, or delivered to the Grants Administration office.

PUBLIC HEARING:

A public hearing was held in the County Council Assembly Room in the Administrative Building, 1003 Highway 52, Moncks Corner, SC 29461 on Thursday September 5th, from 3 to 5 pm to review and discuss the draft CAPER. For more information, call (843) 719-4766.

## CR-45 - CDBG 91.520(c)

Specify the nature of, and reasons for, any changes in the jurisdiction’s program objectives and indications of how the jurisdiction would change its programs as a result of its experiences.

Berkeley County was a new entitlement community receiving CDBG funds for the first time in PY 2021.  PY 2023 is the third year of the County’s 2021-2025 Consolidated Plan and this CAPER reports on activities from July 1, 2023 to June 30, 2024. CDBG priorities and goals remained unchanged. The County does not anticipate any changes to the priorities identified in the ConPlan, and there are no changes in the goals and objectives of the 5-Yr Strategic Plan that would result in the revision of its objectives for CDBG.

CARES Act Funds

As the County was awarded CDBG funds for the first time in PY 2021, there were no CARES Act funds awarded to the County.  Federal CARES Act funds were appropriated in 2020 to assist LMI communities prevent, prepare for, and respond to the COVID-19 pandemic.  While the County did not receive these funds, it will still continue to monitor the needs of citizens as it relates to the pandemic.

Does this Jurisdiction have any open Brownfields Economic Development Initiative (BEDI) grants?

No

## CR-50 - HOME 24 CFR 91.520(d)

Include the results of on-site inspections of affordable rental housing assisted under the program to determine compliance with housing codes and other applicable regulations

Please list those projects that should have been inspected on-site this program year based upon the schedule in 24 CFR §92.504(d). Indicate which of these were inspected and a summary of issues that were detected during the inspection. For those that were not inspected, please indicate the reason and how you will remedy the situation.

As the County has recently been funded with HOME, the County does not have any HOME funded rental development units within the affordability period.  Currently there are no HOME activities requiring long-term monitoring.  Furthermore, the County will be focusing efforts on homeowner housing rehab.

Provide an assessment of the jurisdiction's affirmative marketing actions for HOME units. 24 CFR 91.520(e) and 24 CFR 92.351(a)

The County will promote housing programs to all eligible households and affirmatively furthers fair housing to assure compliance with 24 CFR 92.351.  In PY 2023, there were no HOME contracts of affordable housing activities however when there are housing projects that meet the requirements for affirmative marketing, the County will take the steps to ensure compliance. The purpose affirmative marketing is to communicate to the general public that the County’s housing development programs are administered with equal opportunity and are nondiscriminatory.

HOME WBE/MBE: There were no contracts made to minority or women-owned businesses in PY 2023.

Refer to IDIS reports to describe the amount and use of program income for projects, including the number of projects and owner and tenant characteristics

No HOME program funds were expended and no HOME program income funds were spent in PY 2023. The County contributed $233,132 in HOME program income funds in the previous program year 2022 since that year’s annual allocation in did not meet the initial threshold of $750,000 for the County to become a HOME PJ.  These funds are displayed as the balance on hand at the start of the program year in the CR-15.

Describe other actions taken to foster and maintain affordable housing. 24 CFR 91.220(k) (STATES ONLY: Including the coordination of LIHTC with the development of affordable housing). 24 CFR 91.320(j)

Berkeley County was awarded HOME funds for the first time in Program Year (PY) 2022. The County plans to utilize these funds to support the development of homeownership opportunities for LMI households.

With CDBG funds, the County has funded activities such as infrastructure improvements that have an overall purpose to aid in the development of the affordable housing stock.  This includes development of streets and waterlines that will provide infrastructure for the development of affordable housing developed by County partners such as Habitat for Humanity.

## CR-58 - Section 3

Identify the number of individuals assisted and the types of assistance provided

| Total Labor Hours | CDBG | HOME |
| --- | --- | --- |
| Total Number of Activities | 2 | 0 |
| Total Labor Hours | 2,597 | 0 |
| Total Section 3 Worker Hours | 578 | 0 |
| Total Targeted Section 3 Worker Hours | 0 | 0 |

Table 15 – Total Labor Hours

| Qualitative Efforts - Number of Activities by Program | CDBG | HOME |
| --- | --- | --- |
| Outreach efforts to generate job applicants who are Public Housing Targeted Workers | 0 | 0 |
| Outreach efforts to generate job applicants who are Other Funding Targeted Workers. | 0 | 0 |
| Direct, on-the job training (including apprenticeships). | 0 | 0 |
| Indirect training such as arranging for, contracting for, or paying tuition for, off-site training. | 0 | 0 |
| Technical assistance to help Section 3 workers compete for jobs (e.g., resume assistance, coaching). | 0 | 0 |
| Outreach efforts to identify and secure bids from Section 3 business concerns. | 0 | 0 |
| Technical assistance to help Section 3 business concerns understand and bid on contracts. | 0 | 0 |
| Division of contracts into smaller jobs to facilitate participation by Section 3 business concerns. | 0 | 0 |
| Provided or connected residents with assistance in seeking employment including: drafting resumes, preparing for interviews, finding job opportunities, connecting residents to job placement services. | 0 | 0 |
| Held one or more job fairs. | 2 | 0 |
| Provided or connected residents with supportive services that can provide direct services or referrals. | 0 | 0 |
| Provided or connected residents with supportive services that provide one or more of the following: work readiness health screenings, interview clothing, uniforms, test fees, transportation. | 0 | 0 |
| Assisted residents with finding child care. | 0 | 0 |
| Assisted residents to apply for, or attend community college or a four year educational institution. | 0 | 0 |
| Assisted residents to apply for, or attend vocational/technical training. | 0 | 0 |
| Assisted residents to obtain financial literacy training and/or coaching. | 0 | 0 |
| Bonding assistance, guaranties, or other efforts to support viable bids from Section 3 business concerns. | 0 | 0 |
| Provided or connected residents with training on computer use or online technologies. | 0 | 0 |
| Promoting the use of a business registry designed to create opportunities for disadvantaged and small businesses. | 0 | 0 |
| Outreach, engagement, or referrals with the state one-stop system, as designed in Section 121(e)(2) of the Workforce Innovation and Opportunity Act. | 0 | 0 |
| Other. | 0 | 0 |

Table 16 – Qualitative Efforts - Number of Activities by Program

Narrative

On October 29, 2020 HUD made effective the Final Rule, which set new benchmarks for Section 3 under 24 CFR 75.  Section 3 helps to establish more economically sustainable communities by ensuring that employment and other economic opportunities generated by Federal assistance for development programs are directed towards very low- and low-income persons to the greatest extent possible, and in particular to those who are recipients of the Federal assistance. The Final Rule changes tracking the number of qualified new hires in Section 3 projects, to tracking the total labor hours worked.

As applicable to Berkeley County, the benchmark for Section 3 workers is set at 25 percent or more of the total number of labor hours worked by all workers on a Section 3 project. The benchmark for Targeted Section 3 workers is set at 5 percent or more of the total number of labor hours worked by all workers on a Section 3 project.

Section 3 Projects cover housing rehab/construction and public improvement construction activities assisted under HUD grant programs that provide housing and community development financial assistance which exceed a threshold of $200,000. A $100,000 project threshold applies to grants under HUD's Lead Hazard Control and Healthy Homes programs.  In PY 2023, the County reports a total of 578 hours from Section 3 workers out of 2,597 total hours from two activities.

Activity #14 Habitat for Humanity Affordable Housing was funded for $200,975.25 which met the Section 3 reporting threshold.  Total labor hours performed was 1,195 hours, however there were only 50 Section 3 workers hours and did not meet the 25 percent benchmark.  Safe harbor was met through qualitative efforts which included promoting work through job fairs.

Activity #23 Renovation of American Legion Hut was funded for $231,254.40 which also met the Section 3 reporting threshold.  Total labor hours performed was 1,402 hours, and there were 528 Section 3 workers hours which met the 25 percent benchmark.